WEEK 1 TASK

PROJECT PLANNING AND STRATEGY
FOR AN END-TO-END ML PIPELINE

Student Academic Performance Prediction System

A Python-based Machine Learning Project Plan

Project purpose Design a feasible, measurable and deployment-ready plan for building an ML system that predicts student academic performance from academic, social and study-related attributes. The plan covers problem definition, research, data, modeling, evaluation, deployment, risks and monitoring.

| Item | Plan |
| --- | --- |
| Prepared for | Week 1 ML Pipeline Planning Task |
| Project domain | Education / Educational Data Mining |
| Primary ML task | Classification, with optional regression extension |
| Methodology | CRISP-DM + reproducible Python ML workflow |
| Proposed dataset | UCI Student Performance / Student Academics Performance |
| Planned stack | Python, Pandas, NumPy, scikit-learn, Matplotlib, Seaborn, Flask/FastAPI |
| Estimated Week 1 effort | 30–35 hours |
| Implementation roadmap | 8 weeks |

Prepared: September 2026

# Table of Contents

Contents

Table of Contents	2

1. Introduction	3

2. Research and Ideation	3

2.1 Literature and Methodology Review	3

2.2 Candidate Problem Comparison	3

3. Problem Definition	3

3.1 Problem Statement	3

3.2 Proposed Inputs	3

3.3 Expected Output	4

3.4 Key Challenges	4

3.5 Assumptions and Constraints	4

4. Project Objectives	4

4.1 Success Criteria	4

5. Proposed End-to-End ML Pipeline	5

6. Detailed Technical Strategy	5

6.1 Data Acquisition and Versioning	5

6.2 Data Quality Checks	5

6.3 Exploratory Data Analysis	5

6.4 Preprocessing	6

6.5 Candidate Models	6

6.6 Evaluation Metrics	6

7. Project Timeline and Work Breakdown	6

7.1 Week 1 Detailed Schedule — 30–35 Hours	6

8. Milestones and Acceptance Gates	7

9. Critical Path and Dependencies	7

9.1 Parallelizable Work	7

10. Resource Requirements	8

10.1 Software	8

10.2 Hardware	8

10.3 Human Resources	8

11. Risk Management	8

11.1 Risk Response Strategy	9

12. Data Privacy, Ethics and Responsible ML	9

13. Deployment Strategy	9

13.1 Proposed Architecture	9

13.2 Deployment Steps	9

14. Monitoring and Maintenance Roadmap	9

15. Documentation and Repository Structure	10

15.1 Documentation Checklist	10

16. Strategic Roadmap	10

16.1 Future Enhancements	11

17. Expected Deliverables	11

18. Conclusion	11

References	11

Appendix A — Submission Quality Checklist	12

If page numbers do not refresh, right-click the table of contents in Word and select “Update Field”.

# 1. Introduction

Machine learning projects succeed when the technical solution is connected to a clearly defined problem, measurable objectives, suitable data and an implementation strategy. A model with high laboratory accuracy can still fail in practice if the target is poorly defined, leakage is present, the data is unrepresentative or the deployment environment cannot reproduce the training pipeline.

Educational data mining is a useful project domain because academic outcomes can be studied using structured attributes such as prior performance, study habits, school context and other factors available in public datasets. The proposed project is an academic/research prototype and is not intended to make high-stakes decisions about students.

The project follows the six-phase CRISP-DM lifecycle: business understanding, data understanding, data preparation, modeling, evaluation and deployment. IBM describes CRISP-DM as an industry-proven, non-proprietary way to organize data-mining work, and emphasizes that the phases are iterative rather than strictly linear. [1][2]

# 2. Research and Ideation

## 2.1 Literature and Methodology Review

CRISP-DM was selected as the planning framework because it connects the problem/business objective to data preparation, model development, evaluation and deployment. IBM's CRISP-DM guidance also recommends that a project plan identify tasks, time estimates, resources, deployment effort, risks and decision points. [1][2]

The UCI Machine Learning Repository provides public student-performance datasets appropriate for supervised learning. The UCI Student Performance dataset contains 649 instances and supports both classification and regression. Its documentation highlights a strong correlation between final grade G3 and earlier-period grades G1 and G2, which makes target leakage a central planning issue. [3]

A second UCI dataset, Student Academics Performance, contains 300 instances and 22 features and was created to study end-semester percentage prediction using social, economic and academic attributes. It can serve as an alternative or external validation dataset if the primary dataset is unsuitable. [4]

## 2.2 Candidate Problem Comparison

| Candidate problem | Advantages | Main challenge |
| --- | --- | --- |
| Student academic performance | Public data; clear target; educational relevance | Generalization and responsible use |
| Customer churn | Strong business relevance; many datasets | Business assumptions vary by dataset |
| House price prediction | Simple regression formulation | Market drift and geographic dependence |
| Sales forecasting | Practical business use case | Requires temporal validation and forecasting design |

Selected problem: Student Academic Performance Prediction. The selection is based on feasibility, availability of public data, clear supervised-learning formulation and the opportunity to demonstrate a complete pipeline.

# 3. Problem Definition

## 3.1 Problem Statement

The proposed system will learn patterns from historical student records and predict an academic performance category using information available before the final outcome is known. The primary technical formulation is supervised classification. A secondary regression formulation may be explored if a continuous target can be defined without leakage.

## 3.2 Proposed Inputs

| Input group | Examples | Type | Planning note |
| --- | --- | --- | --- |
| Academic history | Previous academic indicators | Numeric / ordinal | Check for target leakage |
| Study habits | Study time, educational support | Ordinal / categorical | Potentially predictive |
| Attendance-related data | Absences or participation proxies | Numeric | Depends on dataset |
| Family context | Parent education/occupation where available | Categorical | Use cautiously |
| School context | School/support/activity attributes | Categorical | Dataset dependent |
| Demographics | Age or other available non-sensitive attributes | Numeric/categorical | Assess necessity and fairness |

## 3.3 Expected Output

Predicted academic-performance class.

Probability distribution across classes where the selected model supports calibrated probabilities.

Optional predicted continuous score if a leakage-safe regression target is defined.

Basic explanation of influential features for transparency.

## 3.4 Key Challenges

Small or medium-sized public datasets may not generalize to another institution.

Categorical variables require consistent encoding between training and inference.

Target leakage can artificially inflate performance.

Class imbalance can make accuracy misleading.

Historical data can contain biases that are reproduced by a model.

Prediction does not establish causation.

Production inputs may contain missing or unexpected values.

## 3.5 Assumptions and Constraints

The prototype uses public research data.

The project is for academic/research purposes.

Python is the primary implementation language.

The first deployment target is a local or lightweight web/API environment.

A standard student laptop is sufficient; GPU is not required.

# 4. Project Objectives

| ID | Objective | Acceptance evidence |
| --- | --- | --- |
| O1 | Define measurable problem and success criteria | Approved scope and target definition |
| O2 | Acquire and understand suitable public data | Dataset card and data dictionary |
| O3 | Build reproducible preprocessing | Reusable sklearn pipeline |
| O4 | Compare multiple baseline models | Model comparison table |
| O5 | Evaluate with suitable metrics | Validation and final test report |
| O6 | Assess leakage, imbalance and responsible-ML risks | Risk/bias assessment |
| O7 | Package the selected model | Serialized pipeline |
| O8 | Plan and demonstrate deployment | API/web prototype |
| O9 | Document reproducibility | README, requirements and technical report |
| O10 | Define monitoring and future improvement | Monitoring roadmap |

## 4.1 Success Criteria

A complete train/validation/test workflow is reproducible.

Prediction-time information is clearly distinguished from post-outcome information.

At least three suitable ML models are compared.

Classification evaluation includes accuracy, precision, recall, F1-score and confusion matrix; ROC-AUC is included where appropriate.

Cross-validation is used during model selection and the final test set is kept untouched until final evaluation.

The saved pipeline can transform raw inference input and produce a prediction.

A simple API or web interface can load the saved pipeline.

Documentation clearly states limitations and appropriate use.

# 5. Proposed End-to-End ML Pipeline

| Stage | Pipeline component | Main activities |
| --- | --- | --- |
| 1 | Problem understanding | Define user, target, constraints and success criteria |
| 2 | Data acquisition | Download dataset; record source, license and version |
| 3 | Data understanding | Profile schema, distributions, missingness and target |
| 4 | Data preparation | Clean, encode, impute, split and engineer features |
| 5 | EDA | Explore distributions, relationships, outliers and imbalance |
| 6 | Baseline | Dummy baseline and interpretable model |
| 7 | Model development | Train candidate algorithms |
| 8 | Validation/tuning | Cross-validation and hyperparameter search |
| 9 | Evaluation | Final test metrics and error analysis |
| 10 | Packaging | Save preprocessing + model as one artifact |
| 11 | Deployment | API/UI and input validation |
| 12 | Monitoring | Drift, performance and retraining triggers |

Critical design rule Preprocessing must be fitted only on training data and packaged with the model. This reduces leakage and prevents training/inference transformation mismatches.

# 6. Detailed Technical Strategy

## 6.1 Data Acquisition and Versioning

Use the UCI Machine Learning Repository as the primary public source.

Record dataset name, DOI/source, access date, file name and license.

Keep raw data separate from processed data.

Never overwrite the raw dataset during cleaning.

Create a data dictionary for every feature.

## 6.2 Data Quality Checks

| Area | Check | Planned method |
| --- | --- | --- |
| Schema | Column names/types | Automated schema check |
| Missingness | Null count and percentage | Threshold + imputation policy |
| Duplicates | Repeated rows/IDs | Duplicate detection |
| Ranges | Impossible numeric values | Rule-based validation |
| Categories | Unexpected labels | Allowed-category checks |
| Target | Class distribution | Frequency table |
| Leakage | Post-outcome variables | Feature review + domain reasoning |

## 6.3 Exploratory Data Analysis

Univariate analysis of numeric and categorical variables.

Target-class distribution and imbalance assessment.

Correlation analysis for numeric variables.

Grouped analysis of performance by relevant categories.

Outlier review using domain context.

Visualizations that guide feature engineering and model choice.

## 6.4 Preprocessing

Split the data before fitting preprocessing transformations.

Impute missing numeric values where required.

Encode categorical values using a reproducible transformer.

Scale numeric variables for algorithms that benefit from scaling.

Use ColumnTransformer/Pipeline so preprocessing is part of the model artifact.

Use class weights or training-only resampling if imbalance requires it.

## 6.5 Candidate Models

| Model | Role | Reason |
| --- | --- | --- |
| Dummy classifier | Reference baseline | Defines minimum expected performance |
| Logistic Regression | Interpretable baseline | Strong baseline for tabular classification |
| Decision Tree | Nonlinear interpretable model | Easy to inspect rules |
| Random Forest | Tree ensemble | Robust nonlinear baseline |
| Gradient Boosting | Ensemble model | Potentially strong tabular performance |

## 6.6 Evaluation Metrics

| Metric | Meaning | Use |
| --- | --- | --- |
| Accuracy | Correct / total | Balanced classes |
| Precision | Correct positives / predicted positives | Controls false positives |
| Recall | Correct positives / actual positives | Important when missing a class matters |
| F1-score | Harmonic mean of precision and recall | Balanced class-level metric |
| Confusion matrix | Class-by-class errors | Error analysis |
| ROC-AUC | Ranking ability | Binary/multiclass settings where appropriate |

# 7. Project Timeline and Work Breakdown

The project is planned as an eight-week roadmap. Week 1 is the planning deliverable and is estimated at approximately 30–35 hours as required by the task.

| Week | Phase | Major activities | Deliverable | Effort |
| --- | --- | --- | --- | --- |
| 1 | Planning & research | Problem, research, dataset, architecture, risks, schedule | Project plan DOCX | 30–35 h |
| 2 | Data understanding | Acquisition, profiling, data dictionary, EDA | Data audit + EDA notebook | 12–16 h |
| 3 | Data preparation | Cleaning, encoding, split and pipeline | Preprocessing pipeline | 12–16 h |
| 4 | Baseline modeling | Baseline + candidate models | Model comparison v1 | 12–16 h |
| 5 | Tuning & validation | Cross-validation and tuning | Validated model | 14–18 h |
| 6 | Evaluation | Test set, errors, explainability | Evaluation report | 12–16 h |
| 7 | Deployment | API/UI, packaging and tests | Working prototype | 14–18 h |
| 8 | Documentation | README, monitoring and final review | Final package | 12–16 h |

## 7.1 Week 1 Detailed Schedule — 30–35 Hours

| Hours | Activity | Work | Output |
| --- | --- | --- | --- |
| 1–2 | Orientation | Understand requirements and scope | Scope statement |
| 3–5 | Research | Review CRISP-DM and ML lifecycle | Research notes |
| 6–8 | Problem ideation | Compare candidate domains | Selection rationale |
| 9–12 | Dataset research | Inspect UCI options and limitations | Dataset plan |
| 13–17 | Pipeline design | Design data-to-deployment architecture | Pipeline specification |
| 18–22 | Timeline | WBS, milestones, critical path | Project schedule |
| 23–26 | Risk/resource analysis | Technical, data, ethical and delivery risks | Risk register |
| 27–30 | Documentation | Write and format plan | DOC draft |
| 31–35 | Review | Proofread, references, final checks | Final DOCX |

# 8. Milestones and Acceptance Gates

| ID | Milestone | Acceptance gate |
| --- | --- | --- |
| M1 | Problem approved | Target, inputs, users and success criteria documented |
| M2 | Dataset validated | Source, schema, license, quality and leakage reviewed |
| M3 | Pipeline ready | Preprocessing is reproducible |
| M4 | Baseline established | Reference performance recorded |
| M5 | Candidate model selected | Cross-validation comparison completed |
| M6 | Model evaluated | Final test evaluation and error analysis completed |
| M7 | Deployment prototype | API/UI loads the saved pipeline |
| M8 | Final release | Documentation, tests and monitoring plan completed |

# 9. Critical Path and Dependencies

The critical path is primarily Dataset validation → target/leakage definition → preprocessing pipeline → baseline modeling → validation/tuning → final evaluation → packaging → deployment. Major rework in an upstream stage can delay all dependent stages.

| Dependent activity | Depends on | Reason |
| --- | --- | --- |
| Dataset selection | Problem definition | Target and features must match the problem |
| Data profiling | Dataset acquisition | Quality cannot be assessed before obtaining data |
| Preprocessing | Data profiling | Cleaning decisions depend on observed data |
| Modeling | Preprocessing | Models require a consistent feature matrix |
| Final evaluation | Model selection | Test evaluation follows model selection |
| Deployment | Final evaluation | Only an accepted model should be deployed |
| Monitoring | Deployment | Operational monitoring requires an inference path |

## 9.1 Parallelizable Work

Literature review and environment setup can proceed in parallel.

EDA visualization planning can proceed while preprocessing is being finalized.

A deployment skeleton can be built with a placeholder model.

Test-case design can begin before deployment is finished.

# 10. Resource Requirements

## 10.1 Software

| Tool | Purpose |
| --- | --- |
| Python 3.x | Primary programming language |
| Jupyter Notebook / VS Code | Exploration and development |
| Pandas | Data manipulation |
| NumPy | Numerical computation |
| scikit-learn | Preprocessing, modeling, validation and metrics |
| Matplotlib / Seaborn | Visualization |
| Joblib | Pipeline serialization |
| Flask / FastAPI | Deployment/API |
| Git + GitHub | Version control |
| pytest | Automated testing |

## 10.2 Hardware

Minimum 8 GB RAM; 16 GB preferred.

5–10 GB free storage for environment, datasets and artifacts.

CPU-only execution is sufficient.

GPU is not required for the initial tabular project.

Stable internet for public dataset and documentation access.

## 10.3 Human Resources

| Role | Responsibility |
| --- | --- |
| ML developer/data analyst | Data preparation, EDA, modeling and evaluation |
| Project reviewer/mentor | Scope review and milestone feedback |
| Domain reviewer | Educational context and appropriate-use review |
| Deployment reviewer | API/UI and reproducibility checks |

# 11. Risk Management

| ID | Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R1 | Data leakage | High | Very High | Define prediction-time information; perform leakage audit |
| R2 | Small dataset/generalization | High | High | Cross-validation, limitations, second dataset where possible |
| R3 | Class imbalance | Medium | High | Per-class metrics, class weights/resampling inside training |
| R4 | Overfitting | Medium | High | Cross-validation, regularization, simpler baselines |
| R5 | Unexpected inference input | Medium | Medium | Schema validation and robust preprocessing |
| R6 | Privacy/ethical concern | Medium | High | Public/de-identified data; minimize sensitive features |
| R7 | Deployment mismatch | Medium | High | Serialize preprocessing + model; smoke tests |
| R8 | Scope creep | Medium | Medium | Define MVP and change-control rule |
| R9 | Schedule delay | Medium | Medium | Track critical path and maintain buffer |
| R10 | Reproducibility failure | Low | High | requirements.txt, version control and rebuild test |

## 11.1 Risk Response Strategy

Avoid: remove features that are unavailable at prediction time or introduce unacceptable leakage.

Mitigate: add validation, tests, documentation and reproducible preprocessing.

Transfer: prefer established libraries and public repositories over unsupported custom infrastructure.

Accept: document low-impact limitations that cannot reasonably be removed within scope.

# 12. Data Privacy, Ethics and Responsible ML

Student-related prediction can affect real people if deployed irresponsibly. The prototype should therefore be treated as decision support, not an authority. It should not be used to deny educational opportunities, label students permanently or make disciplinary decisions.

Use only data permitted by the dataset's license and documented conditions.

Avoid personally identifying information in the prototype.

Document which variables are used and why.

Check group-level performance where the dataset supports such analysis.

Do not interpret predictive association as causal evidence.

Provide a clear limitations statement.

Keep human review in the loop for consequential real-world use.

# 13. Deployment Strategy

## 13.1 Proposed Architecture

| Layer | Component | Control |
| --- | --- | --- |
| Input | Form or JSON request | Schema validation |
| Preprocessing | Saved sklearn pipeline | Same logic as training |
| Model | Versioned classifier | Validated model artifact |
| Prediction service | Flask/FastAPI | Prediction + probability where supported |
| Presentation | Simple HTML/API client | Clear output and limitations |
| Logging | Application logs | Errors, latency, model version |
| Monitoring | Periodic review | Drift and performance checks |

## 13.2 Deployment Steps

Freeze and document the final training dataset.

Train the final pipeline on approved training data.

Evaluate on the untouched test set.

Serialize the complete preprocessing + model pipeline.

Create an API with input validation.

Create smoke tests using known test cases.

Run locally and verify predictions.

Create requirements.txt and setup instructions.

Deploy to a suitable lightweight environment if required.

Record model version, deployment date and rollback procedure.

# 14. Monitoring and Maintenance Roadmap

| Signal | What to monitor | Suggested cadence |
| --- | --- | --- |
| Input drift | Feature distributions change | Monthly / major data change |
| Prediction drift | Class distribution changes | Monthly |
| Performance drift | Accuracy/F1/recall changes when labels arrive | Each evaluation cycle |
| Data quality | Missing/invalid inputs | Every request/batch |
| Latency/errors | API reliability | Continuous logging |
| Fairness indicators | Group-level performance changes | Periodic review |

Retraining should not be triggered solely because time has passed. Evidence such as data drift, target-distribution changes, deteriorating evaluation metrics or a change in the data-generating process should support a retraining decision. Every new model should pass the same validation and acceptance gates.

# 15. Documentation and Repository Structure

Proposed repository structure:

student-performance-ml/
├── data/
│   ├── raw/
│   └── processed/
├── notebooks/
│   ├── 01_data_understanding.ipynb
│   ├── 02_eda.ipynb
│   └── 03_modeling.ipynb
├── src/
│   ├── data_preprocessing.py
│   ├── train.py
│   ├── evaluate.py
│   └── predict.py
├── app/
│   ├── app.py
│   └── templates/
├── models/
├── tests/
├── reports/
├── requirements.txt
├── README.md
└── .gitignore

## 15.1 Documentation Checklist

Project objective and scope

Dataset source, citation, license and version

Data dictionary

Installation instructions

Dependency/environment versions

Training and inference instructions

Evaluation metrics and results

Known limitations

Ethical/appropriate-use statement

Deployment instructions

Monitoring and retraining strategy

# 16. Strategic Roadmap

| Phase | Focus | Key outcomes | Timing |
| --- | --- | --- | --- |
| A | Foundation | Problem, dataset, data quality and baseline | Weeks 1–3 |
| B | Model development | Model comparison, tuning and validation | Weeks 4–5 |
| C | Trust & evaluation | Final test, errors, explainability and responsible-ML review | Week 6 |
| D | Productization | API/UI, packaging and tests | Week 7 |
| E | Operations | Documentation and monitoring strategy | Week 8 |
| F | Future enhancement | More data, external validation and advanced models | Post-project |

## 16.1 Future Enhancements

Validate on an independent dataset or institutional dataset.

Add longitudinal prediction across academic periods.

Compare calibrated probabilities rather than only hard classes.

Add educator-friendly model explanations.

Build aggregate dashboards without exposing individual identities.

Perform deeper subgroup/fairness analysis.

Containerize with Docker.

Add CI/CD and automated model validation.

Introduce model registry/versioning for production-scale use.

# 17. Expected Deliverables

| ID | Deliverable | Format | Target |
| --- | --- | --- | --- |
| D1 | Week 1 project plan | DOCX | Week 1 |
| D2 | Dataset and data dictionary | CSV + documentation | Week 2 |
| D3 | EDA notebook | Jupyter notebook + figures | Week 2 |
| D4 | Preprocessing pipeline | Python + tests | Week 3 |
| D5 | Model comparison | Notebook/report | Week 4 |
| D6 | Final evaluation | Report + plots | Week 6 |
| D7 | Deployment prototype | Flask/FastAPI app | Week 7 |
| D8 | Final documentation | README + technical report | Week 8 |

# 18. Conclusion

This project plan establishes a structured route from a clearly defined educational prediction problem to a reproducible and deployable machine-learning prototype. Data quality, leakage prevention, evaluation, ethics, deployment and monitoring are treated as core project activities rather than afterthoughts.

The eight-week roadmap provides a realistic sequence while allowing iteration between CRISP-DM phases. The next implementation phase should begin with dataset validation and data understanding before model development. This ensures that later modeling decisions are supported by a documented data foundation, measurable objectives and explicit risk controls.

Final readiness statement At the end of the planning phase, the project has a defined problem, target, candidate data source, technical architecture, success criteria, schedule, critical path, resources, risks, deployment approach and maintenance strategy.

# References

IBM. CRISP-DM View. IBM SPSS Modeler Documentation. Accessed September 2026. https://www.ibm.com/docs/en/spss-modeler/18.6.0?topic=projects-crisp-dm-view

IBM. IBM SPSS Modeler CRISP-DM Guide. IBM Documentation. https://www.ibm.com/docs/en/SS3RA7_18.6.0/pdf/ModelerCRISPDM.pdf

Cortez, P. (2008). Student Performance. UCI Machine Learning Repository. DOI: 10.24432/C5TG7T. https://archive.ics.uci.edu/dataset/320/student%2Bperformance

Hussain, S. (2018). Student Academics Performance. UCI Machine Learning Repository. DOI: 10.24432/C50W30. https://archive.ics.uci.edu/dataset/467/student%2Bacademics%2Bperformance

Yilmaz, N. & Şekeroğlu, B. (2019). Higher Education Students Performance Evaluation. UCI Machine Learning Repository. DOI: 10.24432/C51G82. https://archive.ics.uci.edu/dataset/856/higher%2Beducation%2Bstudents%2Bperformance%2Bevaluation

# Appendix A — Submission Quality Checklist

| Evaluation requirement | Covered |
| --- | --- |
| Problem clearly defined | Yes |
| Inputs and outputs specified | Yes |
| Research/literature review included | Yes |
| Public dataset identified | Yes |
| End-to-end ML pipeline described | Yes |
| Detailed timeline included | Yes |
| Milestones included | Yes |
| Critical path and dependencies included | Yes |
| Resources/software included | Yes |
| Risk management included | Yes |
| Ethics/privacy included | Yes |
| Deployment strategy included | Yes |
| Monitoring/maintenance included | Yes |
| Documentation strategy included | Yes |
| References included | Yes |